## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Manuelle Aseye Ackun |  | m.ackun@alustudent.com
David Chukwuebuka Achibiri |  | d.achibiri@alustudent.com
Rhoda Nicole Umutesi |  | r.umutesi1@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Data Processing and Cleaning | Manuelle Aseye Ackun | 2026-02-18 | Completed | Yes
| Frontend Dashboard Development | David Chukwuebuka Achibiri | 2026-02-18 | Completed | Yes
| Database Design and Implentation | Rhoda Nicole Umutesi | 2026-02-19 | Completed | Yes
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
|  | [Name] | [Date]
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-02-16 | Discuss the requirements of the assignment and divide the work equally amongst ourselves. | Manuelle Aseye Ackun | Manuelle, David, and Rhoda | Breaking down the work into equal parts for everyone | Complete each part and bring to the group for review
2026-02-18 | Go through the progress of each team member's part and offer help if needed | Manuelle Aseye Ackun | Manuelle, | Go through frontend and backend, make sure database is implemented correctly, and split the PDF documentation into parts. | Complete the PDF documentation, make finishing touches to the GitHub Repo, and finish video walkthrough by the deadline
[Date] |  | [Name] | [List of Attendees] | [Summary of Discussion] | [Follow-up Actions]
[Date] |  | [Name] | [List of Attendees] | [Summary of Discussion] | [Follow-up Actions]
[Date] |  | [Name] | [List of Attendees] | [Summary of Discussion] | [Follow-up Actions]